Mentored Grant Writing Program

Updated: January 11, 2021

Research Development Group: Jon Balzotti, Kristen Kellems, Jaynie Mitchell, Aimee Kirlew

With limited success, BYU faculty from every college have submitted proposals to external funders. Faculty who receive external funding provide hands-on learning experiences for students and develop high quality scholarship for themselves. However, government funding for academic research has stagnated and competition for available funds is increasingly fierce. An internal program that trains our faculty to target funding and write winning proposals significantly improves their success at capturing external funding. The Mentored Grant Writing Program will have an immediate impact on the number of proposals written, but more importantly, it will increase the success rate of those proposals.

The objective is to develop a robust grant proposal writing mentoring program that will help BYU faculty obtain funding for their research projects. The participants in this program will be new faculty and those with little experience in proposal writing. They will be mentored faculty who are successful grant proposal writers.

There are three components to the Mentored Grant Writing Program: (1) select and pair mentors to participants, (2) train participants in proposal writing, (3) provide personalized mentoring to participants.

Select and Match Program Participants

Faculty Center will send an email to new faculty involved with the Faculty Development Series to invite them to hone their grant-writing skills by participating in the Mentored Grant Writing Program.  Faculty Center will share those who have expressed interest in the program with Research Development. Research Development (RD) will match participants with mentors who have received external funding. In most cases, these mentors will be the same mentor that new faculty members are assigned to as part of the Faculty Development Series. If the mentor has not had adequate experience applying for external funding, RD will find a new mentor for the participant. Once RD has determined the appropriate matches, we will inform the mentors, participants, and Faculty Center.

Research Development and Faculty Center will collaborate on a “Meet and Greet” in which the participants and mentors meet each other and learn about the requirements of the Mentored Grant-Writing Program. Participants will receive a stipend and a certificate of completion upon finishing the program. Former participants can be future mentors.

Train Participants in Proposal Writing

Throughout the Mentored Grant Writing Program, RD will develop and present seminars and workshops on different elements of proposal writing (including discipline-specific instruction), starting with a seminar on finding external funding in fall semester. During winter semester, participants will attend the “Meet and Greet” with their mentors in which they both meet their mentors and learn about program expectations. In May, participants will attend a 4-day proposal development “bootcamp” workshop that teaches baseline logic and other elements of good proposal writing including how to develop themes and persuasive proposal sections. The goal of the May bootcamp is for participants to develop a first draft of their proposal to an external funder. During the months following the bootcamp, RD will host three meetings for participants and mentors to review and share proposal progress. At the end of the summer, proposals will receive a final review by a faculty panel (selected in coordination with deans and department chairs) prior to submittal to an external funder.

Provide Personalized Mentorship

Throughout the program, the participants will receive advice from their mentors to aid them in all aspects of the grant writing process (e.g., which funders would best fit their research interests; how to approach program officers; and how to capitalize on the mentor’s funder-knowledge to strengthen the participant’s proposal). Through this personalized mentorship, the participants will be successful in navigating the proposal process and capturing funding.

Implementation

The implementation of the proposed program will require RD to:

- Recruit participants, identify mentors and match participants and mentors

- Develop a February mentor/participant meeting with initial proposal writing training

- Provide a 4-day May bootcamp in which mentors participate on the final day

- Develop post-bootcamp proposal review meetings as needed

- Select reviewers and host a final proposal review meeting

The Faculty Center will also provide program advertising to faculty and support for the hosted events.

Cost

Participants will receive $250 for completing May bootcamp and another $250 for submitting an external proposal. Participants will receive $500 in their “20” account for completing both of those requirements and completing the program.

Anticipated Outcomes

The Proposal Writing Mentorship Program should result in the following outcomes for participants:

- Understand the grant proposal process

- Write high quality proposals and have higher proposal success rates

- Become mentors for other faculty

- Be recognized for completing the program (college/university awarded certificate)

- Publish in top-tier journals

Mentors can benefit from this program by:

- Developing more collaborators

- Improving their writing skills

- Act as a consultant or even co-PI on participant’s proposals

- Publish in top-tier journals

BYU faculty are engaged in innovative and forward-moving research. This program will enable our faculty to capture funding that will enhance their own careers and the research profile of the university.